## Closing Task
Employee Code | Task Category | Detailed Monthly Tasks | Reviewed by | Approved by | Preparation | Review | Approval
RIM | Payroll & Personnel | Process and record Payroll, Final Pay, SL Conversions, and early retirement accrual. | CKVC | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Tax & Provisions | Calculate and record the monthly Tax Provision and PPB Provision (performance bonuses). | CKVC | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Rent & Leases | Record recurring monthly Rental Income/Expense and monthly amortization expense for employee hospitalization plans. | CKVC | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Accruals & Expenses | Record accruals for Consultancy Fees and various routine General Expense Accruals.Estimated expense for which a vendor invoice has not yet been received. | CKVC | CKVC | 1 Day | 0.5 Day | 0.5 Day
|  | Process and record Payments for various Cash Advances. Recording the funding/issuance of cash to employees for expected business expenditures. | CKVC | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Prior Period Review | The necessary reversal or adjustment of temporary journal entries created in a previous month. Process reversal entries for the prior month's accruals and reclassifications. | CKVC | CKVC | 1 Day | 0.5 Day | 0.5 Day
BOM | Amortization & Corporate | Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Depreciation, Amortization for vehicles/purchases/LOA, and Amortization for all technology licenses and shared service costs. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Corporate Accruals | Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Insurance | Monthly tracking and recording of premiums for various corporate insurance policies. Record monthly accrual for various Corporate Insurance types and amortize prepaid Health Insurance. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Treasury & Other | Non-operating financial activities including capital structure and compliance. Record monthly bank charges, perform revaluation of foreign currency bank accounts, and record the monthly expense portion of the Omnicom stock option grant. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Prior Period Review | Process reversal entries for all prior month Accruals (e.g., trainings, production/retainers). | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Regional Reporting | Prepare reports for Flash, Wins & Losses and Revenue. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
JPAL | Client Billings | Recognizing revenue and billable costs based on client contracts and project status. Accrue estimated Production, Retainer Fees, Media Commission, Creative Fees, and OOPC. Recording estimated Out-of-Pocket Costs that will eventually be billed to a client. | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| WIP/OOP Management | Reconciling and reclassifying costs to ensure they are correctly categorized as billable (WIP) or internal (OOP). Perform month-end Reclassifications of OOP to WIP (moves client-related expenses to an active project account) and necessary Reclass WIP to OOP (moves costs back if non-billable). | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Amortization & Corporate | Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Amortization of the Business Permit and Amortization of LOA. | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
|  | Accrue estimated monthly Audit Fees. | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
|  | Record monthly Rental Expense/Income related to intercompany transactions. | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
|  | Perform month-end Revaluation of Intercompany Balances. Adjusting intercompany balances to reflect the correct value at the month-end exchange rate. | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| AR Aging - WC | Prepare reports for Working Captital related to AR | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
LAS | CA Liquidations | Process and record Cash Advance (CA) Liquidations for specific project-related expenses. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| AP Aging - WC | Prepare AP Aging report for working captital submission | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| OOP | Prepare HOW's summary report | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Asset & Lease Entries | Recording transactions for financed assets and long-term commitments. Record monthly interest expense on leased assets and process amortization reclassifications for prepaid corporate fees. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Reclassifications | Correcting entries across the general ledger (GL). Process required reclassifications between specific GL accounts and between Marketing Expense categories. | BOM | CKVC | 1 Day | 0.5 Day | 0.5 Day
JLI | VAT & Taxes | Compile and record monthly Input VAT entries (VAT paid on purchases) and the monthly VAT Report (cumulative summary of VAT activity). | JPAL | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Accruals & Assets | Recording estimated expenses for recurring monthly costs and recognizing non-fixed asset costs. Accrue recurring Expenses (estimated expense for regularly occurring services). | LAS | CKVC | 1 Day | 0.5 Day | 0.5 Day
|  | Record the monthly recognition/capitalization of Other Computer Related Costs. | LAS | CKVC | 1 Day | 0.5 Day | 0.5 Day
| AP Aging | Prepare AP Aging report with detailed status per invoice. | LAS | CKVC | 1 Day | 0.5 Day | 0.5 Day
RMQB | CA Liquidations | Process and record Cash Advance (CA) Liquidations submitted by employees. | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Accruals & Assets | Accrue monthly expense for Employee Cellphone Allowance | LAS | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Expense Reclassification | Adjusting a recorded expense from one GL account to another to ensure correct reporting. Process reclassifications to correct expense categories (e.g., General Expense to Wireless and Meals). | RIM | CKVC | 1 Day | 0.5 Day | 0.5 Day
JAP | VAT Reporting | Compile, review, and record the monthly VAT Report (Initial and additional entries). | JPAL | CKVC | 1 Day | 0.5 Day | 0.5 Day
| Job Transfers | Adjusting costs or revenues between different internal project codes or job numbers. Process and record Transfers of Job Codes for consultancy fees and corporate projects. | JPAL | CKVC | 1 Day | 0.5 Day | 0.5 Day
|  | Record specific GL reclassifications needed for month-end adjustments | JPAL | CKVC | 1 Day | 0.5 Day | 0.5 Day
JRMO | Accruals | Compile documents for the attachment of the revenue accruals. | JPAL | CKVC | 1 Day | 0.5 Day | 0.5 Day
| WIP | Prepare WIP schedule summary per Job# | JPAL | CKVC | 1 Day | 0.5 Day | 0.5 Day

## Closing Task - Gannt Chart
Task Category | Detailed Task | Activity | Employee | Date | Email
I. Initial & Compliance | Payroll Processing & Tax Provision
I. Initial & Compliance | 1. Process and record Payroll, Final Pay, SL Conversions, and early retirement accrual. | Preparation | RIM | 2025-10-24 | rey.meran@omc.com
I. Initial & Compliance | 1. Process and record Payroll, Final Pay, SL Conversions, and early retirement accrual. | Review | RIM (SFM) | 2025-10-27 | rey.meran@omc.com
I. Initial & Compliance | 1. Process and record Payroll, Final Pay, SL Conversions, and early retirement accrual. | Approval | CKVC (FD) | 2025-10-27 | khalil.veracruz@omc.com
I. Initial & Compliance | 2. Calculate and record the monthly Tax Provision and PPB Provision (performance bonuses). | Preparation | RIM | 2025-10-27 | rey.meran@omc.com
I. Initial & Compliance | 2. Calculate and record the monthly Tax Provision and PPB Provision (performance bonuses). | Review | RIM (SFM) | 2025-10-28 | rey.meran@omc.com
I. Initial & Compliance | 2. Calculate and record the monthly Tax Provision and PPB Provision (performance bonuses). | Approval | CKVC (FD) | 2025-10-28 | khalil.veracruz@omc.com
I. Initial & Compliance | VAT Data/Filing
I. Initial & Compliance | 1. Compile, review, and record the monthly VAT Report (Initial and additional entries). | Preparation | JAP | 2025-10-27 | jasmin.ignacio@omc.com
I. Initial & Compliance | 1. Compile, review, and record the monthly VAT Report (Initial and additional entries). | Review | JPAL | 2025-10-28 | jinky.paladin@omc.com
I. Initial & Compliance | 1. Compile, review, and record the monthly VAT Report (Initial and additional entries). | Approval | RIM (SFM) | 2025-10-28 | rey.meran@omc.com
I. Initial & Compliance | 2. Compile and record monthly Input VAT entries (VAT paid on purchases) and the monthly VAT Report (cumulative summary of VAT activity). | Preparation | JIL | 2025-10-27 | jerald.loterte@omc.com
I. Initial & Compliance | 2. Compile and record monthly Input VAT entries (VAT paid on purchases) and the monthly VAT Report (cumulative summary of VAT activity). | Review | JPAL | 2025-10-28 | jinky.paladin@omc.com
I. Initial & Compliance | 2. Compile and record monthly Input VAT entries (VAT paid on purchases) and the monthly VAT Report (cumulative summary of VAT activity). | Approval | RIM (SFM) | 2025-10-28 | rey.meran@omc.com
I. Initial & Compliance | CA Liquidations (All)
I. Initial & Compliance | 1. Process and record Cash Advance (CA) Liquidations for specific project-related expenses. | Preparation | LAS | 2025-10-27 | amor.lasaga@omc.com
I. Initial & Compliance | 1. Process and record Cash Advance (CA) Liquidations for specific project-related expenses. | Review | RIM (SFM) | 2025-10-29 | rey.meran@omc.com
I. Initial & Compliance | 1. Process and record Cash Advance (CA) Liquidations for specific project-related expenses. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
I. Initial & Compliance | 2. Process and record Cash Advance (CA) Liquidations submitted by employees. | Preparation | RMQB | 2025-10-27 | sally.brillantes@omc.com
I. Initial & Compliance | 2. Process and record Cash Advance (CA) Liquidations submitted by employees. | Review | RIM (SFM) | 2025-10-29 | rey.meran@omc.com
I. Initial & Compliance | 2. Process and record Cash Advance (CA) Liquidations submitted by employees. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | Accruals (Revenue/Fees)
II. Accruals & Amortization | 1. Record accruals for Consultancy Fees and various routine General Expense Accruals.Estimated expense for which a vendor invoice has not yet been received. | Preparation | RIM | 2025-10-28 | rey.meran@omc.com
II. Accruals & Amortization | 1. Record accruals for Consultancy Fees and various routine General Expense Accruals.Estimated expense for which a vendor invoice has not yet been received. | Review | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 1. Record accruals for Consultancy Fees and various routine General Expense Accruals.Estimated expense for which a vendor invoice has not yet been received. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 2. Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | Preparation | BOM | 2025-10-27 | beng.manalo@omc.com
II. Accruals & Amortization | 2. Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | Review | RIM | 2025-10-28 | rey.meran@omc.com
II. Accruals & Amortization | 2. Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | Approval | CKVC (FD) | 2025-10-28 | khalil.veracruz@omc.com
II. Accruals & Amortization | 3. Recognizing revenue and billable costs based on client contracts and project status. Accrue estimated Production, Retainer Fees, Media Commission, Creative Fees, and OOPC. Recording estimated Out-of-Pocket Costs that will eventually be billed to a client. | Preparation | JPAL | 2025-10-27 | jinky.paladin@omc.com
II. Accruals & Amortization | 3. Recognizing revenue and billable costs based on client contracts and project status. Accrue estimated Production, Retainer Fees, Media Commission, Creative Fees, and OOPC. Recording estimated Out-of-Pocket Costs that will eventually be billed to a client. | Review | BOM | 2025-10-27 | beng.manalo@omc.com
II. Accruals & Amortization | 3. Recognizing revenue and billable costs based on client contracts and project status. Accrue estimated Production, Retainer Fees, Media Commission, Creative Fees, and OOPC. Recording estimated Out-of-Pocket Costs that will eventually be billed to a client. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 4. Recording estimated expenses for recurring monthly costs and recognizing non-fixed asset costs. Accrue recurring Expenses (estimated expense for regularly occurring services). | Preparation | LAS | 2025-10-28 | amor.lasaga@omc.com
II. Accruals & Amortization | 4. Recording estimated expenses for recurring monthly costs and recognizing non-fixed asset costs. Accrue recurring Expenses (estimated expense for regularly occurring services). | Review | RIM | 2025-10-29 | rey.meran@omc.com
II. Accruals & Amortization | 4. Recording estimated expenses for recurring monthly costs and recognizing non-fixed asset costs. Accrue recurring Expenses (estimated expense for regularly occurring services). | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 5. Record the monthly recognition/capitalization of Other Computer Related Costs. | Preparation | LAS | 2025-10-28 | amor.lasaga@omc.com
II. Accruals & Amortization | 5. Record the monthly recognition/capitalization of Other Computer Related Costs. | Review | RIM | 2025-10-29 | rey.meran@omc.com
II. Accruals & Amortization | 5. Record the monthly recognition/capitalization of Other Computer Related Costs. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 6. Accrue monthly expense for Employee Cellphone Allowance | Preparation | RMQB | 2025-10-27 | sally.brillantes@omc.com
II. Accruals & Amortization | 6. Accrue monthly expense for Employee Cellphone Allowance | Review | RIM | 2025-10-28 | rey.meran@omc.com
II. Accruals & Amortization | 6. Accrue monthly expense for Employee Cellphone Allowance | Approval | CKVC (FD) | 2025-10-28 | khalil.veracruz@omc.com
II. Accruals & Amortization | 7. Compile documents for the attachment of the revenue accruals. | Preparation | JOL | 2025-10-29 | jhoee.oliva@omc.com
II. Accruals & Amortization | Amortizations (IT/Fixed Assets)
II. Accruals & Amortization | 1. Record recurring monthly Rental Income/Expense and monthly amortization expense for employee hospitalization plans. | Preparation | RIM | 2025-10-28 | rey.meran@omc.com
II. Accruals & Amortization | 1. Record recurring monthly Rental Income/Expense and monthly amortization expense for employee hospitalization plans. | Review | RIM | 2025-10-29 | rey.meran@omc.com
II. Accruals & Amortization | 1. Record recurring monthly Rental Income/Expense and monthly amortization expense for employee hospitalization plans. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 2. Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Depreciation, Amortization for vehicles/purchases/LOA, and Amortization for all technology licenses and shared service costs. | Preparation | BOM | 2025-10-28 | beng.manalo@omc.com
II. Accruals & Amortization | 2. Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Depreciation, Amortization for vehicles/purchases/LOA, and Amortization for all technology licenses and shared service costs. | Review | RIM | 2025-10-29 | rey.meran@omc.com
II. Accruals & Amortization | 2. Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Depreciation, Amortization for vehicles/purchases/LOA, and Amortization for all technology licenses and shared service costs. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 3. Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | Preparation | BOM | 2025-10-29 | beng.manalo@omc.com
II. Accruals & Amortization | 3. Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | Review | RIM | 2025-10-30 | rey.meran@omc.com
II. Accruals & Amortization | 3. Accrue monthly expenses for Management and Royalty fees, consulting fees, and funds for Innovations/Initiatives. Brief Detail: Recognizing an expense for internal projects or strategic corporate investments not yet formally invoiced. | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
II. Accruals & Amortization | 4. Monthly tracking and recording of premiums for various corporate insurance policies. Record monthly accrual for various Corporate Insurance types and amortize prepaid Health Insurance. | Preparation | BOM | 2025-10-29 | beng.manalo@omc.com
II. Accruals & Amortization | 4. Monthly tracking and recording of premiums for various corporate insurance policies. Record monthly accrual for various Corporate Insurance types and amortize prepaid Health Insurance. | Review | RIM | 2025-10-30 | rey.meran@omc.com
II. Accruals & Amortization | 4. Monthly tracking and recording of premiums for various corporate insurance policies. Record monthly accrual for various Corporate Insurance types and amortize prepaid Health Insurance. | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
II. Accruals & Amortization | 5. Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Amortization of the Business Permit and Amortization of LOA. | Preparation | JPAL | 2025-10-28 | jinky.paladin@omc.com
II. Accruals & Amortization | 5. Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Amortization of the Business Permit and Amortization of LOA. | Review | BOM | 2025-10-29 | beng.manalo@omc.com
II. Accruals & Amortization | 5. Allocating prepaid expenses and capital costs over time to reflect true monthly resource consumption. Record monthly Amortization of the Business Permit and Amortization of LOA. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 6. Accrue estimated monthly Audit Fees. | Preparation | JPAL | 2025-10-28 | jinky.paladin@omc.com
II. Accruals & Amortization | 6. Accrue estimated monthly Audit Fees. | Review | BOM | 2025-10-29 | beng.manalo@omc.com
II. Accruals & Amortization | 6. Accrue estimated monthly Audit Fees. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 7. Record monthly Rental Expense/Income related to intercompany transactions. | Preparation | JPAL | 2025-10-28 | jinky.paladin@omc.com
II. Accruals & Amortization | 7. Record monthly Rental Expense/Income related to intercompany transactions. | Review | BOM | 2025-10-29 | beng.manalo@omc.com
II. Accruals & Amortization | 7. Record monthly Rental Expense/Income related to intercompany transactions. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 8. Perform month-end Revaluation of Intercompany Balances. Adjusting intercompany balances to reflect the correct value at the month-end exchange rate. | Preparation | JPAL | 2025-10-28 | jinky.paladin@omc.com
II. Accruals & Amortization | 8. Perform month-end Revaluation of Intercompany Balances. Adjusting intercompany balances to reflect the correct value at the month-end exchange rate. | Review | BOM | 2025-10-29 | beng.manalo@omc.com
II. Accruals & Amortization | 8. Perform month-end Revaluation of Intercompany Balances. Adjusting intercompany balances to reflect the correct value at the month-end exchange rate. | Approval | CKVC (FD) | 2025-10-29 | khalil.veracruz@omc.com
II. Accruals & Amortization | 9. Recording transactions for financed assets and long-term commitments. Record monthly interest expense on leased assets and process amortization reclassifications for prepaid corporate fees. | Preparation | LAS | 2025-10-29 | amor.lasaga@omc.com
II. Accruals & Amortization | 9. Recording transactions for financed assets and long-term commitments. Record monthly interest expense on leased assets and process amortization reclassifications for prepaid corporate fees. | Review | RIM | 2025-10-30 | rey.meran@omc.com
II. Accruals & Amortization | 9. Recording transactions for financed assets and long-term commitments. Record monthly interest expense on leased assets and process amortization reclassifications for prepaid corporate fees. | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
III. WIP | WIP/OOP Reconciliation
III. WIP | 1. Reconciling and reclassifying costs to ensure they are correctly categorized as billable (WIP) or internal (OOP). Perform month-end Reclassifications of OOP to WIP (moves client-related expenses to an active project account) and necessary Reclass WIP to OOP (moves costs back if non-billable). | Preparation | JPAL | 2025-10-29 | jinky.paladin@omc.com
III. WIP | 1. Reconciling and reclassifying costs to ensure they are correctly categorized as billable (WIP) or internal (OOP). Perform month-end Reclassifications of OOP to WIP (moves client-related expenses to an active project account) and necessary Reclass WIP to OOP (moves costs back if non-billable). | Review | RIM | 2025-10-30 | rey.meran@omc.com
III. WIP | 1. Reconciling and reclassifying costs to ensure they are correctly categorized as billable (WIP) or internal (OOP). Perform month-end Reclassifications of OOP to WIP (moves client-related expenses to an active project account) and necessary Reclass WIP to OOP (moves costs back if non-billable). | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
III. WIP | 2. Prepare WIP schedule summary per Job# | Preparation | JRMO | 2025-10-28 | joana.maravillas@omc.com
III. WIP | 2. Prepare WIP schedule summary per Job# | Review | JPAL | 2025-10-29 | jinky.paladin@omc.com
III. WIP | 2. Prepare WIP schedule summary per Job# | Approval | BOM | 2025-10-29 | beng.manalo@omc.com
IV. Final Adjustments & Close | 1. The necessary reversal or adjustment of temporary journal entries created in a previous month. Process reversal entries for the prior month's accruals and reclassifications. | Preparation | RIM | 2025-10-29 | rey.meran@omc.com
IV. Final Adjustments & Close | 1. The necessary reversal or adjustment of temporary journal entries created in a previous month. Process reversal entries for the prior month's accruals and reclassifications. | Review | RIM | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 1. The necessary reversal or adjustment of temporary journal entries created in a previous month. Process reversal entries for the prior month's accruals and reclassifications. | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 2. Process reversal entries for all prior month Accruals (e.g., trainings, production/retainers). | Preparation | BOM | 2025-10-29 | beng.manalo@omc.com
IV. Final Adjustments & Close | 2. Process reversal entries for all prior month Accruals (e.g., trainings, production/retainers). | Review | RIM | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 2. Process reversal entries for all prior month Accruals (e.g., trainings, production/retainers). | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 3. Prepare reports for Flash, Wins & Losses and Revenue. | Preparation | BOM | 2025-10-30 | beng.manalo@omc.com
IV. Final Adjustments & Close | 3. Prepare reports for Flash, Wins & Losses and Revenue. | Review | RIM (SFM) | 2025-11-03 | rey.meran@omc.com
IV. Final Adjustments & Close | 3. Prepare reports for Flash, Wins & Losses and Revenue. | Approval | CKVC (FD) | 2025-11-03 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 4. Prepare reports for Working Captital related to AR | Preparation | JPAL | 2025-10-30 | jinky.paladin@omc.com
IV. Final Adjustments & Close | 4. Prepare reports for Working Captital related to AR | Review | BOM | 2025-11-03 | beng.manalo@omc.com
IV. Final Adjustments & Close | 4. Prepare reports for Working Captital related to AR | Approval | CKVC (FD) | 2025-11-03 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 5. Prepare AP Aging report for working captital submission | Preparation | LAS | 2025-10-30 | amor.lasaga@omc.com
IV. Final Adjustments & Close | 5. Prepare AP Aging report for working captital submission | Review | RIM | 2025-11-03 | rey.meran@omc.com
IV. Final Adjustments & Close | 5. Prepare AP Aging report for working captital submission | Approval | CKVC (FD) | 2025-11-03 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 6. Prepare HOW's summary report | Preparation | LAS | 2025-10-29 | amor.lasaga@omc.com
IV. Final Adjustments & Close | 6. Prepare HOW's summary report | Review | RIM | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 6. Prepare HOW's summary report | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 7.Correcting entries across the general ledger (GL). Process required reclassifications between specific GL accounts and between Marketing Expense categories. | Preparation | LAS | 2025-10-30 | amor.lasaga@omc.com
IV. Final Adjustments & Close | 7.Correcting entries across the general ledger (GL). Process required reclassifications between specific GL accounts and between Marketing Expense categories. | Review | RIM | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 7.Correcting entries across the general ledger (GL). Process required reclassifications between specific GL accounts and between Marketing Expense categories. | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 8. Prepare AP Aging report with detailed status per invoice. | Preparation | JLI | 2025-10-29 | jerald.loterte@omc.com
IV. Final Adjustments & Close | 8. Prepare AP Aging report with detailed status per invoice. | Review | LAS | 2025-10-30 | amor.lasaga@omc.com
IV. Final Adjustments & Close | 8. Prepare AP Aging report with detailed status per invoice. | Approval | RIM | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 9. Adjusting a recorded expense from one GL account to another to ensure correct reporting. Process reclassifications to correct expense categories (e.g., General Expense to Wireless and Meals). | Preparation | RMBQ | 2025-10-30 | sally.brillantes@omc.com
IV. Final Adjustments & Close | 9. Adjusting a recorded expense from one GL account to another to ensure correct reporting. Process reclassifications to correct expense categories (e.g., General Expense to Wireless and Meals). | Review | RIM | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 9. Adjusting a recorded expense from one GL account to another to ensure correct reporting. Process reclassifications to correct expense categories (e.g., General Expense to Wireless and Meals). | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 10. Adjusting costs or revenues between different internal project codes or job numbers. Process and record Transfers of Job Codes for consultancy fees and corporate projects. | Preparation | JAP | 2025-10-30 | jasmin.ignacio@omc.com
IV. Final Adjustments & Close | 10. Adjusting costs or revenues between different internal project codes or job numbers. Process and record Transfers of Job Codes for consultancy fees and corporate projects. | Review | JPAL | 2025-10-30 | jinky.paladin@omc.com
IV. Final Adjustments & Close | 10. Adjusting costs or revenues between different internal project codes or job numbers. Process and record Transfers of Job Codes for consultancy fees and corporate projects. | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com
IV. Final Adjustments & Close | 11. Final TB Review | Review | RIM (SFM) | 2025-10-30 | rey.meran@omc.com
IV. Final Adjustments & Close | 12. Final TB Sign-off & Filing | Approval | CKVC (FD) | 2025-10-30 | khalil.veracruz@omc.com

## Tax Filing
BIR Form | Period Covered | BIR Filing & Payment Deadline (2026) | 1. Prep & File Request (Finance Supervisor) | 2. Report Approval (Senior Finance Manager) | 3. Payment Approval (Finance Director)
1601-C (Compensation) | 2025-12-01 | 2025-01-15 | 2025-01-09 | 2025-01-13 | 2025-01-14
1601-C / 0619-E | 2026-01-01 | 2025-02-10 | 2025-02-04 | 2025-02-06 | 2025-02-07
1601-C / 0619-E | 2026-02-01 | 2025-03-10 | 2025-03-04 | 2025-03-06 | 2025-03-07
1601-C / 0619-E | 2026-03-01 | 2025-04-10 | 2025-04-04 | 2025-04-08 | 2025-04-09
1601-C / 0619-E | 2026-04-01 | 2025-05-10 | 2025-05-06 | 2025-05-08 | 2025-05-09
1601-C / 0619-E | 2026-05-01 | 2025-06-10 | 2025-06-04 | 2025-06-06 | 2025-06-09
1601-C / 0619-E | 2026-06-01 | 2025-07-10 | 2025-07-04 | 2025-07-08 | 2025-07-09
1601-C / 0619-E | 2026-07-01 | 2025-08-10 | 2025-08-05 | 2025-08-07 | 2025-08-08
1601-C / 0619-E | 2026-08-01 | 2025-09-10 | 2025-09-04 | 2025-09-08 | 2025-09-09
1601-C / 0619-E | 2026-09-01 | 2026-10-12 | 2026-10-06 | 2026-10-08 | 2026-10-09
1601-C / 0619-E | 2026-10-01 | 2025-11-10 | 2025-11-04 | 2025-11-06 | 2025-11-07
1601-C / 0619-E | 2026-11-01 | 2025-12-10 | 2025-12-03 | 2025-12-05 | 2025-12-09
1601-EQ (Quarterly EWT) | Q4 2025 | 2025-01-30 | 2025-01-24 | 2025-01-28 | 2025-01-29
1702-RT/EX (Income Tax) | Annual 2025 | 2025-04-15 | 2025-04-09 | 2025-04-11 | 2025-04-14
2550Q (VAT) | Q1 2026 | 2026-04-27 | 2026-04-21 | 2026-04-23 | 2026-04-24
1601-EQ (Quarterly EWT) | Q1 2026 | 2025-04-30 | 2025-04-24 | 2025-04-28 | 2025-04-29
2550Q (VAT) | Q2 2026 | 2026-07-27 | 2026-07-21 | 2026-07-23 | 2026-07-24
1702Q (Quarterly Income Tax) | Q2 2026 | 2025-05-30 | 2025-05-26 | 2025-05-28 | 2025-05-29
1601-EQ (Quarterly EWT) | Q2 2026 | 2025-07-31 | 2025-07-25 | 2025-07-29 | 2025-07-30
2550Q (VAT) | Q3 2026 | 2026-10-26 | 2026-10-20 | 2026-10-22 | 2026-10-23
1702Q (Quarterly Income Tax) | Q3 2026 | 2025-08-29 | 2025-08-25 | 2025-08-27 | 2025-08-28
1601-EQ (Quarterly EWT) | Q3 2026 | 2025-10-30 | 2025-10-24 | 2025-10-28 | 2025-10-29
Step | Process Detail | Target Completion | Responsible Role |  | Email
1. Preparation | Gather data, prepare the BIR Form, and draft the payment request (e.g., check voucher). | BIR Deadline - 4 Business Days | Finance Supervisor | BOM | beng.manalo@omc.com
2. Report Approval | Senior Finance Manager (SFM) reviews and approves the report data for accuracy and compliance. (File Request is submitted to SFM.) | BIR Deadline - 2 Business Days | Senior Finance Manager | RIM | rey.meran@omc.com
3. Payment Approval | The approved report and payment request are routed. Finance Director (FD) reviews and approves the release of funds for remittance. | BIR Deadline - 1 Business Day | Finance Director | CKVC | khalil.veracruz@omc.com
4. Filing & Payment | The approved form is Filed and the payment is Remitted (either electronically or over the counter). | On or before the BIR Deadline | Finance Supervisor | BOM | beng.manalo@omc.com

## Holidays & Calendar
Date | Holiday Name | Type | WORKDAY CALCULATOR |  |  | DYNAMIC CLOSING PERIOD DEADLINES
2025-12-08 | Feast of the Immaculate Conception | Special Non-Working | Deadline Date: | 2026-01-15 | ← Enter deadline here | Today's Date: | 2025-12-30
2025-12-24 | Christmas Eve | Special Non-Working | Days Before: | -4 | ← Negative = before deadline | Closing Month: | 2025-11-30 | ← Previous month end
2025-12-25 | Christmas Day | Regular Holiday | Working Day Result: | 46031 | ← Skips weekends & holidays | Closing Deadline: | 2025-12-29 | ← Last working day of current month
2025-12-30 | Rizal Day | Regular Holiday
2025-12-31 | Last Day of the Year | Special Non-Working | FORMULA TO USE: | =WORKDAY(deadline,-days,holidays) |  | INPUT: Select Closing Period
2026-01-01 | New Year's Day | Regular Holiday | Holiday Range: | Holidays & Calendar'!$A$2:$A$46 |  | Closing Year: | 2025 | ← Enter year
2026-02-17 | Chinese New Year | Special Non-Working |  |  |  | Closing Month: | 12 | ← Enter month (1-12)
2026-03-20 | Eid'l Fitr (End of Ramadan) | Regular Holiday | EXAMPLE: Tax Filing Deadlines | Formula | Description | Period End Date: | 2025-12-31 | ← Auto-calculated
2026-04-02 | Maundy Thursday | Regular Holiday | Prep (-4 days) | =WORKDAY(C2,-4,Holidays) | 4 business days before deadline | Soft Close (WD-5): | 2025-12-19 | ← 5 working days before
2026-04-03 | Good Friday | Regular Holiday | Review (-2 days) | =WORKDAY(C2,-2,Holidays) | 2 business days before deadline | Hard Close: | 2026-02-04 | ← WD+3 of next month
2026-04-04 | Black Saturday | Special Non-Working | Approval (-1 day) | =WORKDAY(C2,-1,Holidays) | 1 business day before deadline
2026-04-09 | Araw ng Kagitingan | Regular Holiday |  |  |  | Task Category | Task | Days | Deadline | Day | Status
2026-05-01 | Labor Day | Regular Holiday | Note: Add new holidays to column A to automatically adjust all dates |  |  | I. Initial & Compliance | Payroll & Tax Provision | -5 | 2025-12-19 | Fri | ✓ Done
2026-05-27 | Eid'l Adha (Feast of Sacrifice) | Regular Holiday |  |  |  |  | VAT Data/Filing | -4 | 2025-12-22 | Mon | ✓ Done
2026-06-12 | Independence Day | Regular Holiday |  |  |  |  | CA Liquidations | -4 | 2025-12-22 | Mon | ✓ Done
2026-08-21 | Ninoy Aquino Day | Special Non-Working |  |  |  | II. Accruals & Amortization | Revenue Accruals | -3 | 2025-12-23 | Tue | ✓ Done
2026-08-31 | National Heroes Day | Regular Holiday |  |  |  |  | Expense Accruals | -3 | 2025-12-23 | Tue | ✓ Done
2026-11-01 | All Saints' Day | Special Non-Working |  |  |  |  | Depreciation & Amortization | -2 | 2025-12-26 | Fri | ✓ Done
2026-11-02 | All Souls' Day | Special Non-Working |  |  |  |  | Insurance & Corporate | -2 | 2025-12-26 | Fri | ✓ Done
2026-11-30 | Bonifacio Day | Regular Holiday |  |  |  |  | Intercompany Transactions | -2 | 2025-12-26 | Fri | ✓ Done
2026-12-08 | Feast of the Immaculate Conception | Special Non-Working |  |  |  | III. WIP/Reconciliation | WIP/OOP Reconciliation | -1 | 2025-12-29 | Mon | ✓ Done
2026-12-24 | Christmas Eve | Special Non-Working |  |  |  |  | AP/AR Aging Reports | -1 | 2025-12-29 | Mon | ✓ Done
2026-12-25 | Christmas Day | Regular Holiday |  |  |  | IV. Final Close | Prior Period Reversals | 0 | 2025-12-31 | Wed | Pending
2026-12-30 | Rizal Day | Regular Holiday |  |  |  |  | GL Reclassifications | 1 | 2026-01-02 | Fri | Pending
2026-12-31 | Last Day of the Year | Special Non-Working |  |  |  |  | Flash Reports | 2 | 2026-01-05 | Mon | Pending
2027-01-01 | New Year's Day | Regular Holiday |  |  |  |  | Working Capital Reports | 3 | 2026-01-06 | Tue | Pending
2027-02-08 | Chinese New Year | Special Non-Working |  |  |  | V. Sign-off | Final TB Review (SFM) | 4 | 2026-01-07 | Wed | Pending
2027-03-10 | Eid'l Fitr (End of Ramadan) | Regular Holiday |  |  |  |  | Final TB Sign-off (FD) | 5 | 2026-01-08 | Thu | Pending
2027-03-25 | Maundy Thursday | Regular Holiday |  |  |  |  | Regional Submission | 6 | 2026-01-09 | Fri | Pending
2027-03-26 | Good Friday | Regular Holiday
2027-03-27 | Black Saturday | Special Non-Working |  |  |  | TAX FILING DEADLINES
2027-04-09 | Araw ng Kagitingan | Regular Holiday |  |  |  | BIR Form | Description | BIR Deadline | Prep (-4 WD) | Review (-2 WD) | Approval (-1 WD)
2027-05-01 | Labor Day | Regular Holiday |  |  |  | 1601-C / 0619-E | Monthly Withholding Tax | 2026-01-10 | 2026-01-06 | 2026-01-08 | 2026-01-09
2027-05-16 | Eid'l Adha (Feast of Sacrifice) | Regular Holiday |  |  |  | 2550M | Monthly VAT | 2026-01-20 | 2026-01-14 | 2026-01-16 | 2026-01-19
2027-06-12 | Independence Day | Regular Holiday
2027-08-21 | Ninoy Aquino Day | Special Non-Working |  |  |  | QUARTERLY (if applicable)
2027-08-30 | National Heroes Day | Regular Holiday |  |  |  | 1601-EQ | Quarterly Expanded W/Tax | 2026-01-31 | 2026-01-27 | 2026-01-29 | 2026-01-30
2027-11-01 | All Saints' Day | Special Non-Working |  |  |  | 2550Q | Quarterly VAT | 2026-01-25 | 2026-01-20 | 2026-01-22 | 2026-01-23
2027-11-02 | All Souls' Day | Special Non-Working |  |  |  | 1702Q | Quarterly Income Tax | N/A | N/A | N/A | N/A
2027-11-30 | Bonifacio Day | Regular Holiday
2027-12-08 | Feast of the Immaculate Conception | Special Non-Working |  |  |  | ANNUAL (if December)
2027-12-24 | Christmas Eve | Special Non-Working |  |  |  | 1702-RT/EX | Annual Income Tax Return | 2026-04-15 | 2026-04-08 | 2026-04-13 | 2026-04-14
2027-12-25 | Christmas Day | Regular Holiday |  |  |  | 1604-CF | Annual Info Return (Compensation) | 2026-01-31 | 2026-01-27 | 2026-01-29 | 2026-01-30
2027-12-30 | Rizal Day | Regular Holiday |  |  |  | 1604-E | Annual Info Return (Expanded) | 2026-03-01 | 2026-02-24 | 2026-02-26 | 2026-02-27
2027-12-31 | Last Day of the Year | Special Non-Working
LEGEND:
[6 empty] | Closing Tasks: | Days = working days relative to period end (negative=before, positive=after)
[6 empty] | Tax Filing: | Prep/Review/Approval = working days before BIR deadline
[6 empty] | Status: | N/A = not applicable for selected month (quarterly/annual forms)
[6 empty] | To change period: | Edit J7 (year) and J8 (month) → ALL deadlines auto-update!
Formulas:
Deadline = WORKDAY(J9,[Days],A2:A46)
Deadline = WORKDAY([Days],-4,A2:A46)
Day = WORKDAY([Days],-2,A2:A46)
Day = IF([Days]="N/A","N/A",WORKDAY([Days],-2,A2:A46))
Status = WORKDAY([Days],-1,A2:A46)
Status = IF([Days]="N/A","N/A",WORKDAY([Days],-1,A2:A46))